Mark progress - Choose "☑ Done" when complete
## Plan
Day #	Date	Category	Task	Acceptance Criteria (Definition of Done)	Handy Commands / Notes	Done
1	2025-08-12	Auth / Sessions	Add `sessions` table migration (with indexes)	Goose migration applied; `sessions` table visible in pgAdmin; indexes: UNIQUE(refresh_token_hash), idx(user_id), idx(expires_at or partial on active).	goose -dir sql/schema postgres "$DB_URL" up ; psql "$DB_URL" -c '\d sessions'	☑ Done
1	2025-08-12	Auth / OpenAPI	Extend OpenAPI: /auth/signup, /auth/login, /auth/refresh, /auth/logout, /auth/me	api.yaml updated; oapi-codegen generates server stubs without errors; docs render in Swagger UI.		☐ To do
2	2025-08-13	Auth Implementation	Implement signup (create user+employee, hash password)	POST /auth/signup returns 201; user row exists; default account_role=employee.		☐ To do
2	2025-08-13	Auth Implementation	Implement login (verify hash, create session, mint tokens)	POST /auth/login returns access JWT (15m) + refresh token; session row created with future expires_at.		☐ To do
2	2025-08-13	Middleware	JWT auth middleware + role guard	Protected routes reject missing/invalid tokens; RequireRole('manager') allows manager/admin only.		☐ To do
3	2025-08-14	Auth Implementation	Implement refresh (rotate refresh tokens)	Old refresh cannot be reused; new session row created; old session revoked; returns new access+refresh.		☐ To do
3	2025-08-14	Auth Implementation	Implement logout & logout-all	Logout revokes current session; logout-all revokes all sessions for user; subsequent refresh fails.		☐ To do
3	2025-08-14	Bootstrap Admin	Startup bootstrap to create first admin from env	On fresh DB, server logs 'admin created'; subsequent restarts log 'skipped'.	ENV: ADMIN_EMAIL, ADMIN_PASSWORD	☐ To do
3	2025-08-14	Health	Add /healthz and /readyz endpoints	Both return 200; readyz checks DB connection.		☐ To do
4	2025-08-15	Seed Data	Write `sql/seed/seed.sql` for templates + role counts (idempotent)	Running `make seed` truncates & reloads 14 templates + template_roles without duplicates.	make seed	☐ To do
4	2025-08-15	Templates API	GET /templates (templates + nested role counts)	Returns 200 with seeded data; matches OpenAPI schema; example added to docs.	curl /templates	☐ To do
5	2025-08-16	Schedule Schema	Add `shifts` + `shift_assignments` migrations	Tables exist; constraints: UNIQUE(shift_id, employee_id) ; idx(shifts.shift_date) ; idx(assignments.shift_id, role).		☐ To do
5	2025-08-16	Docs	Update README quickstart + curl for auth/templates	README updated; Postman/Insomnia collection exported.		☐ To do
6	2025-08-17	Generate Week	Add POST /weeks:generate (input monday date)	Endpoint returns 201; inserts shifts for 7 days per active template; pre-creates assignment slots.		☐ To do
6	2025-08-17	Idempotency	Guard against re-generation for same Monday	Calling generate twice yields the same row counts; no duplicates.		☐ To do
7	2025-08-18	Schedule Read	GET /schedule?week=YYYY-MM-DD	Returns all shifts in the week with arrays of slots (filled & vacant).		☐ To do
7	2025-08-18	Overnights	Support shifts spanning midnight	Shifts where end_time < start_time are treated as next-day; documented rule; tests pass.		☐ To do
8	2025-08-19	Assignments	POST /assignments (fill/create a slot)	Filling a slot sets employee_id; rejects double-book in same shift (409).		☐ To do
8	2025-08-19	Assignments	PATCH /assignments/{id} & DELETE /assignments/{id}	PATCH updates employee/role/status; DELETE frees the slot; all validations enforced.		☐ To do
9	2025-08-20	Permissions	Account roles + route guards (employee/manager/admin)	Employee can view schedule & create requests only; manager/admin can generate/assign.		☐ To do
9	2025-08-20	Change Requests	Add change_requests table + endpoints (POST, GET mine, approve/reject)	Employees can have at most 1 pending request (partial unique); manager approval mutates assignments atomically.		☐ To do
10	2025-08-21	Validation & Errors	Consistent 400/401/403/404/409 error model	All handlers return structured JSON errors per spec; invalid inputs yield 400 with details.		☐ To do
10	2025-08-21	Logging	Structured request/response logs with request_id & user_id	Logs show per-request correlation; panic recovery enabled.		☐ To do
11	2025-08-22	Docs	Serve Swagger/Redoc at /docs with examples for every endpoint	UI loads; examples copy-paste work; schemas match responses.		☐ To do
11	2025-08-22	CORS/Config	CORS for future frontend; env-driven config; graceful shutdown	Allowed origins set for dev; SIGTERM shuts down cleanly.		☐ To do
12	2025-08-23	Testing	Integration tests: auth flow + generate week + schedule read	CI can spin Postgres, run migrations, seed, then tests; all green.		☐ To do
12	2025-08-23	Testing	Unit tests: generator idempotency & conflict checks	Edge cases covered (duplicate generation, double-book).		☐ To do
13	2025-08-24	CI	GitHub Actions: DB service, goose up, tests, vet/staticcheck	Badge (optional) in README; PRs run the pipeline automatically.		☐ To do
13	2025-08-24	Makefile	Add `reset` target (down -all → up → migrate → seed)	`make reset` rebuilds a clean dev DB and reseeds in one command.		☐ To do
14	2025-08-25	Polish / Buffer	Bugfix buffer, README polish, Postman/Insomnia export committed	Final smoke test of all endpoints; README has curl for each route; repo ready to share.		☐ To do